## Sheet1
Team: | 3D | Andri Friðriksson - anf4@hi.is - 141190-2379 - Will be doing the presentation. | Unit: person-days (assuming 2 productive hours per person-day)
Ása Júlía Aðalsteinsdóttir - aja11@hi.is - 030896-2549.
Einar Andreas Helgason - eah8@hi.is - 180282-7269.
Sigurlaug Þórðardóttir - sth301@hi.is - 150295-3279.
Sprint | User Story ID | User Story | Estimated Team Effort | Priority | Actual Team Effort | Done?
1 | 6 | As a traveler, I want to see how long the day trip takes because I have limited time in Iceland and I want to plan everything well. | 0.5 | 10 | … | ...
1 | 1 | As a traveler, I want to be able to choose a certain day trip with regard to a specific time and date for my travels because I will only be staying in Iceland for a limited time. | 4.0 | 10
1 | 2 | As a traveler, I want to be able to choose a certain type of day trips. I want to be able to narrow down my search based on my interests. | 3.0 | 20
1 | 9 | As a traveler I want to be able to search for day trips at a specific location so that I see day trips that are in my area. | 3.0 | 30
1 | 4 | As a traveler, I want to be able to search day trips witihin a specific price range so that it will match my budget. | 4.0 | 40
1 | 14 | As a traveller, I want to be able to book a tour online so I have secured my place in the tour and don't have to go through other trouble. | 8.0 | 50
2 | 18 | As a traveller, I want to be able to cancel my bookings so my plans are flexible in case something comes up. | 4.0 | 60
2 | 10 | As a travel agent I want to be able to book more than one person at once to save time and not do the same thing again and again. | 4.0 | 70
2 | 12 | As a traveler I would like to see how many places are available on a particular day trip so I can choose a trip that has enough places. | 3.0 | 80
2 | 3 | As a traveler, I want to be able to request a hotel pickup so that I will not have to rent a car or worry about other expenses regarding commuting. | 2.0 | 90
2 | 16 | As a parent whose children are on a specific day tour, I want to be able to find the contact details for the tour company so I can check in on them. | 1.0 | 100
2 | 8 | As a traveler, I want to be able to choose family friendly or accessible tours so that I take part in the whole tour. | 1.0 | 100
2 | 5 | As a traveler, I want to be able to access the search bar at all stages of the booking process so that I may cancel or change my mind at any time. | 2.0 | 100
2 | 11 | As a travel agent I want to see how many people can be booked on a particular day trip so I have an idea of how large the group will be. | 1.0 | 110
Other | 17 | As a traveller, I want to be able to review my past bookings so I can I recommend specific trips to my friends. | 6.0 | 120
Other | 7 | As a user, I want to rate the day trips I have been on so I can help other users with choosing a trip. | 20.0 | 130
Other | 13 | As a tour planner I want to be able to register my tour so that people can find it in the search engine. | 10.0 | 130
Other | 15 | As a traveller, I want to be able to pay for a tour online so that I don't have to worry about doing it later. | 20.0 | 140

## Sheet2
Model
Gagnagrunnur
View
GUI
Controller
| Search | getByFilter()
Bookings
| - Breytur: | bookerName
tripId
numTravelers
hotelPickup
bookingStatus
| - Föll: | book()
cancel()
Trips
| - Breytur: | tripId
tripName
date
startTime
endTime
description
familyFriendly
accessible
price
tripType
tripArea
tripLocation
maxTravelers
isFull?
availablePlaces
tourCompanyId
| - Föll: | create() / register()
Tour company
| - Breytur: | companyName
companyId
- Föll:
getName()
getAddress()
getEmail()
Hotel Pickup??